## Sheet1
Risk ID | Risk Description | Likelihood | Impact | Risk Level | Existing Controls | Mitigation Plan | Risk Owner | Review Date
1 | Unauthorized network access | High | High | High | Firewall, strong passwords | Implement MFA, network segmentation | IT Security | 2025-09-01
2 | Phishing attack leading to data breach | Medium | High | Medium | Email filtering, user training | Conduct phishing simulations, enhance email filtering | Security Awareness Team | 2025-09-15
3 | Server hardware failure | Medium | Medium | Medium | RAID storage, backups | Improve monitoring and alerts | Infrastructure | 2025-08-30
4 | Insider threat | Low | High | Medium | Access controls, monitoring | Implement stricter role reviews | HR & Security | 2025-10-01
5 | Data loss due to ransomware | Medium | High | High | Endpoint protection, backups | Regular backup testing, patch management | IT Operations | 2025-09-20